## Landsone Shine
S. No. | Activity/ Particulars | Start date | End date
1 | Excavation | 2023-06-01 | 2023-07-01 | 30
2 | Plinth | 2023-08-01 | 2023-12-01 | 122
3 | RCC | 2023-12-01 | 2025-01-01 | 397
4 | Blockwork | 2025-01-01 | 2025-04-01 | 90
5 | Internal Plaster | 2025-02-01 | 2025-05-01 | 89
6 | External Plaster | 2025-03-01 | 2025-06-01 | 92
7 | Water Proofing | 2025-04-01 | 2025-06-01 | 61
8 | Flooring & Tiling Work | 2025-05-01 | 2025-07-01 | 61
9 | Electrical | 2025-06-01 | 2025-08-01 | 61
10 | Plumbing & Drainages Works | 2025-07-01 | 2025-09-01 | 62
11 | Fire Fighting | 2025-08-01 | 2025-10-01 | 61
12 | Lift | 2025-09-01 | 2025-11-01 | 61
13 | Aluminium Window | 2025-10-01 | 2025-12-01 | 61
14 | VDO Door, Phone & Frame | 2025-11-01 | 2026-01-01 | 61
15 | Fabrication | 2025-12-01 | 2026-02-01 | 62
16 | False Ceiling | 2026-01-01 | 2026-03-01 | 59
17 | Painting | 2026-02-01 | 2026-04-01 | 59
18 | Amenities | 2026-05-01 | 2026-06-01 | 31
1096

## Sheet1
Phase | Level | Activity / Component | Start Date | End Date | Duration | Key Notes
1. Site Preparation | — | Clearing, survey, layout, temporary utilities | {start_date_str} | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Includes barricading, soil testing
Plinth |  | Heavy and stable base for Building | end date of Site Preparation | Write the end date Depending on Activity / Component column
2. Excavation & Raft | B1 Basement | Deep excavation, retaining walls, raft PCC & waterproofing | end date of Site Preparation | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | 1-level excavation with dewatering
3. RCC Superstructure | B1 Basement | Raft → slab | end date of Site Preparation | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Raft PCC, waterproofing and B1 slab (overlaps excavation)
| Keep on increasing basement based on {num_basements} | Columns → slab | end date of RCC Superstructure | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date
| Ground Floor | Columns → slab | end date of RCC Superstructure | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Podium + entry level
| 1st Floor | Columns → slab | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Begin MEP embedments
| Keep on increasing floors based on num_floors_above based on {num_basements} | Columns → slab | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Structural cycle stabilized
| Terrace / Roof Slab | Roof slab & parapet | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | End of structural cycle
4. Masonry & Plastering | B1, GF – max floor | Blockwork, lintels, internal & external plaster | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Start two floors below RCC front
5. Basement Services | B1 Basement | Waterproofing, ramps, driveways, STP, sump | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Coordinate with RCC progress
6. Electrical / Plumbing (1st Fix) | All Levels | Concealed conduits, sleeves, piping | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Parallel with masonry
7. Flooring & Tiling | GF – max floor | Screed, tiles, skirting, toilets | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Start after plastering floor-wise
8. Waterproofing (Terrace & Wet Areas) | Roof + B1 + Wet areas | APP membrane, toilets, balconies | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Critical quality stage
9. Painting & Finishes | B1, GF – max floor | Putty, primer, internal/external paint | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Interior & façade
10. Fixtures & Fit-outs | All Levels | Doors, windows, sanitary, lighting | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Overlap with painting
11. External Development | Site / Podium | Compound wall, paving, drainage, landscaping | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Coordinate with façade
12. Testing & Handover | Entire Project | Lift, fire, STP, electrical, final cleaning | Based on progreess of prior construction | Write the end date Depending on Activity / Component column | Calculate total days rquired to fininsh this phase based on Start date and End date | Occupancy & completion certificate

## Construction Progress
80%
[6 empty] | Miscellinious | Plinth | Basement |  | Ground Floor | Podium | Upper Floor | Total Slab
23.44% | B | 1 | 0.23438 | 3.947% | 3.947% |  |  | 1 |  | 1 | 1 | 13 | 16
23.44% | G | 1 | 0.23438 | 3.947% | 3.947% | 5% | 15%
21.87% | P | 1 | 0.21875 | 3.684% | 3.684%
31.25% | UF | 13 | 4.0625 | 68.42% | 5.263%
4.75
[6 empty] | 80% |  | Floor | Slab | Residential/Commercial/Parking & No. of Units | Construction Work | Complete Status | Percentage of Work Completed | Construction Progress
[8 empty] | Plinth |  |  | Excavation and Foundation Construction | completed | 100% | 15%
[11 empty] | Plinth Beam and Masonry | completed | 100%
[11 empty] | Backfilling and Compaction | completed | 100% |  | No basement | 10%
[11 empty] | Waterproofing and Damp Proof Course (DPC) | completed | 100% |  | if there is basement | 15%
[8 empty] | Basement | 1st Slab | Parking | Basement Floor Slab Casting, Basement Walls, Plastering | completed | 100% | 3.947%
[11 empty] | Basement Walls | completed | 100%
[11 empty] | Internal Plaster | completed | 100%
[8 empty] | Ground | 2nd Slab | Parking | Basement Floor Slab Casting, Basement Walls, Plastering | completed | 100% | 3.947%
[11 empty] | Basement Walls | completed | 100%
[11 empty] | Internal Plaster | completed | 100%
[8 empty] | Podium | 3rd Slab | Parking | Basement Floor Slab Casting, Basement Walls, Plastering | completed | 100% | 3.684%
[11 empty] | Basement Walls | completed | 100%
[11 empty] | Internal Plaster | completed | 100%
[8 empty] | 1st Floor | 4TH Slab | Residential (12 units) | Floor Slab Casting, Column construction | Completed | 100% | 1.504%
[11 empty] | Wall Construction | completed | 100%
[11 empty] | Internal Plaster | Not Started Yet | 0%
[11 empty] | External Plaster | Not Started Yet | 0%
[11 empty] | Flooring Work | Not Started Yet | 0%
[11 empty] | Painting work | Not Started Yet | 0%
[11 empty] | Finishing work (Ceiling Work, Electrical Installations, Plumbing and Sanitary Installations, Fixture and Fittings, Exterior Finishing) | Not Started Yet | 0%
[8 empty] | 2nd Floor | 5th Slab | Residential (12 units) | Floor Slab Casting, Column construction | completed | 100% | 1.504%
[11 empty] | Wall Construction | completed | 100%
[11 empty] | Internal Plaster | Not Started Yet | 0%
[11 empty] | External Plaster | Not Started Yet | 0%
[11 empty] | Flooring Work | Not Started Yet | 0%
[11 empty] | Painting work | Not Started Yet | 0%
[11 empty] | Finishing work (Ceiling Work, Electrical Installations, Plumbing and Sanitary Installations, Fixture and Fittings, Exterior Finishing) | Not Started Yet | 0%
[8 empty] | 3rd Floor | 6th Slab | Residential (12 units) | Floor Slab Casting, Column construction | completed | 100% | 1.504%
[11 empty] | Wall Construction | completed | 100%
[11 empty] | Internal Plaster | Not Started Yet | 0%
[11 empty] | External Plaster | Not Started Yet | 0%
[11 empty] | Flooring Work | Not Started Yet | 0%
[11 empty] | Painting work | Not Started Yet | 0%
[11 empty] | Finishing work (Ceiling Work, Electrical Installations, Plumbing and Sanitary Installations, Fixture and Fittings, Exterior Finishing) | Not Started Yet | 0%
[8 empty] | 4th Floor | 7th Slab | Residential (12 units) | Floor Slab Casting, Column construction | completed | 100% | 1.504%
[11 empty] | Wall Construction | completed | 100%
[11 empty] | Internal Plaster | Not Started Yet | 0%
[11 empty] | External Plaster | Not Started Yet | 0%
[11 empty] | Flooring Work | Not Started Yet | 0%
[11 empty] | Painting work | Not Started Yet | 0%
[11 empty] | Finishing work (Ceiling Work, Electrical Installations, Plumbing and Sanitary Installations, Fixture and Fittings, Exterior Finishing) | Not Started Yet | 0%
[8 empty] | 5th Floor | 8th Slab | Residential (12 units) | Floor Slab Casting, Column construction | completed | 100% | 0.7519%
[11 empty] | Wall Construction | Not Started Yet | 0%
[11 empty] | Internal Plaster | Not Started Yet | 0%
[11 empty] | External Plaster | Not Started Yet | 0%
[11 empty] | Flooring Work | Not Started Yet | 0%
[11 empty] | Painting work | Not Started Yet | 0%
[11 empty] | Finishing work (Ceiling Work, Electrical Installations, Plumbing and Sanitary Installations, Fixture and Fittings, Exterior Finishing) | Not Started Yet | 0%
[8 empty] | 6th Floor | 9th Slab | Residential (12 units) | Floor Slab Casting, Column construction | completed | 100% | 0.7519%
[11 empty] | Wall Construction | Not Started Yet | 0%
[11 empty] | Internal Plaster | Not Started Yet | 0%
[11 empty] | External Plaster | Not Started Yet | 0%
[11 empty] | Flooring Work | Not Started Yet | 0%
[11 empty] | Painting work | Not Started Yet | 0%
[11 empty] | Finishing work (Ceiling Work, Electrical Installations, Plumbing and Sanitary Installations, Fixture and Fittings, Exterior Finishing) | Not Started Yet | 0%
[8 empty] | 7th Floor | 10th Slab | Residential (12 units) | Floor Slab Casting, Coloumn constrution | completed | 100% | 0.7519%
[11 empty] | Wall Construction | Not Started Yet | 0%
[11 empty] | Internal Plaster | Not Started Yet | 0%
[11 empty] | External Plaster | Not Started Yet | 0%
[11 empty] | Flooring Work | Not Started Yet | 0%
[11 empty] | Painting work | Not Started Yet | 0%
[11 empty] | Finishing work (Ceiling Work, Electrical Installations, Plumbing and Sanitary Installations, Fixture and Fittings, Exterior Finishing) | Not Started Yet | 0%
[8 empty] | 8th Floor | 11th Slab | Residential (12 units) | Floor Slab Casting, Coloumn constrution | completed | 100% | 0.7519%
[11 empty] | Wall Construction | Not Started Yet | 0%
[11 empty] | Internal Plaster | Not Started Yet | 0%
[11 empty] | External Plaster | Not Started Yet | 0%
[11 empty] | Flooring Work | Not Started Yet | 0%
[11 empty] | Painting work | Not Started Yet | 0%
[11 empty] | Finishing work (Ceiling Work, Electrical Installations, Plumbing and Sanitary Installations, Fixture and Fittings, Exterior Finishing) | Not Started Yet | 0%
[8 empty] | 9th Floor | 12th Slab | Residential (12 units) | Floor Slab Casting, Coloumn constrution | completed | 100% | 0.7519%
[11 empty] | Wall Construction | Not Started Yet | 0%
[11 empty] | Internal Plaster | Not Started Yet | 0%
[11 empty] | External Plaster | Not Started Yet | 0%
[11 empty] | Flooring Work | Not Started Yet | 0%
[11 empty] | Painting work | Not Started Yet | 0%
[11 empty] | Finishing work (Ceiling Work, Electrical Installations, Plumbing and Sanitary Installations, Fixture and Fittings, Exterior Finishing) | Not Started Yet | 0%
[8 empty] | Miscellaneous Work |  |  | Sample Flat | Completed | 100% | 2%
[11 empty] | Internal Road | Completed | 100%
[11 empty] | Compounds Wall | Completed | 100%
[11 empty] | Site Office | Completed | 100%
[12 empty] | Total Constrution Progress |  | 38.35% | for Miscellenious work | 5%
[11 empty] | Basement | 1
[11 empty] | Ground Floor | 1
[11 empty] | Podium | 1
[11 empty] | Upper Floors | 13
[11 empty] | Total Slab | 16
15
3.9474
0.039474
0.036842
0.015038
0.015038
0.015038
0.015038
0.0075188
0.0075188
0.0075188
0.0075188
0.0075188
0.02

## Solasta
CONSTRUCTION | START | END DATE
ACTIVITY | DATE
Excavation | 2023-03-01 | 2023-04-01
Plinth | 2023-03-01 | 2023-04-01
RCC work | 2023-01-01 | 2024-01-01
Brick Work | 2023-05-01 | 2024-05-01
Internal Plaster | 2023-08-01 | 2024-06-01
External plaster | 2024-05-01 | 2024-11-01
Flooring And Tiling Work | 2024-11-01 | 2025-04-01
Water Proofing | 2023-10-01 | 2025-04-01
Plumbing And Drainages Work | 2023-09-01 | 2024-11-01
Electric Work | 2023-06-01 | 2023-12-01
Fabrication | 2023-07-01 | 2024-07-01
Fire Fighting | 2024-11-01 | Apl-25
VDO Door, phone And Frame | 2024-11-01 | 2025-02-01
Window & Fitting | 2024-11-01 | 2025-03-01
Amenities | 2025-01-01 | 2025-07-01
Painting Work | 2024-07-01 | 2025-12-01
(Internal And External)
Lift | 2025-01-01 | 2025-07-01
Application for OC and | 2025-09-01 | 2025-12-01
Other completion
formalities

## Navyam
S. No. | Activity/ Particulars | Start date | End date
1 | Excavation & Land Development | 2023-11-01 | 2024-05-01
2 | Footing & Plinth | 2023-12-01 | 2024-06-01
3 | RCC Work | 2024-06-01 | 2025-11-01
4 | Brick work | 2024-08-01 | 2026-01-01
5 | Plaster work | 2024-08-01 | 2026-01-01
6 | Flooring & Tiling Work | 2025-08-01 | 2026-03-01
7 | Water proofing | 2025-07-01 | 2026-02-01
8 | Plumbing & Drainages Works | 2025-08-01 | 2026-03-01
9 | Electric Work | 2025-11-01 | 2026-05-01
10 | Door & Windows | 2026-01-01 | 2026-03-01
11 | Painting Work | 2026-02-01 | 2026-04-01
12 | Garden, other amenities & Development work | 2026-02-01 | 2026-04-01
S. No. | Activity/ Particulars | Start date | End date
1 | Excavation & Land Development | 2023-11-01 | 2024-05-01
2 | Footing & Plinth | 2023-12-01 | 2024-06-01
3 | RCC Work | 2024-06-01 | 2025-11-01
4 | Brick work | 2024-08-01 | 2026-01-01
5 | Plaster work | 2024-08-01 | 2026-01-01
6 | Flooring & Tiling Work | 2025-08-01 | 2026-03-01
7 | Water proofing | 2025-07-01 | 2026-02-01
8 | Plumbing & Drainages Works | 2025-08-01 | 2026-03-01
9 | Electric Work | 2025-11-01 | 2026-05-01
10 | Door & Windows | 2026-01-01 | 2026-03-01
11 | Painting Work | 2026-02-01 | 2026-04-01
12 | Garden, other amenities & Development work | 2026-02-01 | 2026-04-01

## Aura Avenue
S. No. | Activity/Particulars | Start Date | End Date
1 | Excavation | 2025-06-01 | 2025-10-01
2 | Plinth | 2025-10-01 | 2025-12-01
3 | RCC | 2025-12-01 | 2026-12-01
4 | Block-work | 2026-01-01 | 2027-02-01
5 | Internal Plaster | 2026-02-01 | 2027-03-01
6 | External Plaster | 2027-01-01 | 2028-01-01
7 | Water Proofing | 2027-01-01 | 2028-01-01
8 | Flooring & Tiling Work | 2026-02-01 | 2028-05-01
9 | Electrical | 2026-06-01 | 2028-05-01
10 | Plumbing & Drainage Works | 2026-07-01 | 2028-05-01
11 | Fire Fighting | 2026-08-01 | 2028-06-01
12 | Lift | 2028-05-01 | 2028-08-01
13 | Aluminium Window | 2028-01-01 | 2028-05-01
14 | VDO Door, Phone & Frame | 2028-03-01 | 2028-06-01
15 | Fabrication | 2027-02-01 | 2028-04-01
16 | False Ceiling | 2027-07-01 | 2028-03-01
17 | Painting | 2028-02-01 | 2028-08-01
18 | Amenities | 2028-06-01 | 2028-09-01