## Sheet1
Phase | Level | Activity / Component | Start Date | End Date | Duration | Key Notes
1. Site Preparation | — | Clearing, survey, layout, temporary utilities | 2025-10-06 | 2025-10-18 | 2 weeks | Includes barricading, soil testing
2. Excavation & Raft | 4 Basements | Deep excavation, retaining walls, raft PCC & waterproofing | 2025-10-19 | 2026-01-25 | 14 weeks | 4-level excavation with ramp & dewatering
3. RCC Superstructure | B4 Basement | Raft → slab | 2026-01-26 | 2026-02-15 | 3 weeks | 1st cycle begins
| B3 Basement | Columns → slab | 2026-02-16 | 2026-03-08 | 3 weeks | Overlap with waterproofing of B4
| B2 Basement | Columns → slab | 2026-03-09 | 2026-03-30 | 3 weeks | Ramp & MEP shafts coordinated
| B1 Basement | Columns → slab | 2026-03-31 | 2026-04-20 | 3 weeks | Services shafts, parking floor
| Ground Floor | Columns → slab | 2026-04-21 | 2026-05-15 | 3½ weeks | Podium + entry level
| 1st Floor | Columns → slab | 2026-05-16 | 2026-06-10 | 3½ weeks | Begin MEP embedments
| 2nd Floor | Columns → slab | 2026-06-11 | 2026-07-05 | 3½ weeks | Structural cycle stabilised
| 3rd Floor | Columns → slab | 2026-07-06 | 2026-07-30 | 3½ weeks | Overlap finishing below
| 4th Floor | Columns → slab | 2026-07-31 | 2026-08-25 | 3½ weeks | Roof to follow
| Terrace / Roof Slab | Roof slab & parapet | 2026-08-26 | 2026-09-15 | 3 weeks | End of structural cycle
4. Masonry & Plastering | GF – 4th Flr | Blockwork, lintels, internal & external plaster | 2026-06-01 | 2026-10-31 | 5 months | Start two floors below RCC front
5. Basement Services | B4 – B1 | Waterproofing, ramps, driveways, STP, sump | 2026-05-01 | 2026-08-31 | 4 months | Coordinate with RCC progress
6. Electrical / Plumbing (1st Fix) | All Levels | Concealed conduits, sleeves, piping | 2026-06-01 | 2026-09-30 | 4 months | Parallel with masonry
7. Flooring & Tiling | GF – 4th Flr | Screed, tiles, skirting, toilets | 2026-08-01 | 2026-11-30 | 4 months | Start after plastering floor-wise
8. Waterproofing (Terrace & Wet Areas) | Roof + Basements | APP membrane, toilets, balconies | 2026-09-15 | 2026-10-15 | 1 month | Critical quality stage
9. Painting & Finishes | GF – 4th Flr | Putty, primer, internal/external paint | 2026-10-01 | 2026-12-15 | 2½ months | Interior & façade
10. Fixtures & Fit-outs | All Levels | Doors, windows, sanitary, lighting | 2026-11-15 | 2026-12-31 | 1½ months | Overlap with painting
11. External Development | Site / Podium | Compound wall, paving, drainage, landscaping | 2026-11-15 | 2026-12-31 | 1½ months | Coordinate with façade
12. Testing & Handover | Entire Project | Lift, fire, STP, electrical, final cleaning | 2027-01-01 | 2027-01-31 | 1 month | Occupancy & completion certificate